## Issues Report
Issue ID | Control ID | Issue Title | Issue Description | Severity | Issue Status | Issue Owner | Business Unit | Identified Date | Target Remediation Date | Days Open | Root Cause
ISS-2001 | CTRL-1017 | Control Owner Attestation Missing | Recovery Procedure Gap identified during recurring control monitoring activities. | Medium | Past Due | Skyler Martinez | Risk Management | 2026-03-21 | 2026-05-05 | 80 | Process Gap
ISS-2002 | CTRL-1023 | Delayed Approval Workflow | Late Remediation Action identified during recurring control monitoring activities. | Low | Open | Morgan Garcia | Compliance | 2026-01-25 | 2026-03-11 | 135 | Resource Constraint
ISS-2003 | CTRL-1022 | Data Validation Exception | Recovery Procedure Gap identified during recurring control monitoring activities. | Medium | Open | Skyler Wilson | Finance | 2026-02-27 | 2026-05-28 | 102 | Data Quality Issue
ISS-2004 | CTRL-1046 | Data Validation Exception | Data Validation Exception identified during recurring control monitoring activities. | Critical | Open | Skyler Thomas | Risk Management | 2025-12-13 | 2026-01-12 | 178 | Resource Constraint
ISS-2005 | CTRL-1047 | Recovery Procedure Gap | Missing Review Evidence identified during recurring control monitoring activities. | Low | Open | Quinn Anderson | Risk Management | 2025-11-10 | 2025-12-10 | 211 | Data Quality Issue
ISS-2006 | CTRL-1024 | Delayed Approval Workflow | Data Validation Exception identified during recurring control monitoring activities. | Critical | Remediated | Harper Martin | Finance | 2026-01-22 | 2026-04-22 | 48 | System Limitation
ISS-2007 | CTRL-1048 | Unresolved System Exception | Incomplete Control Documentation identified during recurring control monitoring activities. | High | Past Due | Skyler Taylor | Enterprise Resilience | 2026-01-28 | 2026-04-28 | 132 | Policy Misalignment
ISS-2008 | CTRL-1028 | Data Validation Exception | Manual Process Dependency identified during recurring control monitoring activities. | Critical | In Progress | Skyler Anderson | Compliance | 2026-02-13 | 2026-03-15 | 116 | System Limitation
ISS-2009 | CTRL-1004 | Access Review Not Completed | Late Remediation Action identified during recurring control monitoring activities. | High | Remediated | Jamie Smith | Risk Management | 2025-11-02 | 2026-01-01 | 23 | Data Quality Issue
ISS-2010 | CTRL-1029 | Incomplete Control Documentation | Data Validation Exception identified during recurring control monitoring activities. | Critical | Open | Kendall Anderson | Enterprise Resilience | 2025-10-28 | 2026-02-25 | 224 | Human Error
ISS-2011 | CTRL-1037 | Unresolved System Exception | Recovery Procedure Gap identified during recurring control monitoring activities. | Low | Closed | Jamie Robinson | Risk Management | 2026-02-18 | 2026-04-04 | 59 | System Limitation
ISS-2012 | CTRL-1042 | Unresolved System Exception | Missing Review Evidence identified during recurring control monitoring activities. | High | In Progress | Morgan White | Risk Management | 2026-01-10 | 2026-04-10 | 150 | Data Quality Issue
ISS-2013 | CTRL-1048 | Data Validation Exception | Unresolved System Exception identified during recurring control monitoring activities. | Low | Remediated | Emerson White | Compliance | 2025-10-03 | 2025-11-02 | 42 | Policy Misalignment
ISS-2014 | CTRL-1009 | Late Remediation Action | Incomplete Control Documentation identified during recurring control monitoring activities. | Critical | Remediated | Logan Davis | Technology | 2025-09-04 | 2025-12-03 | 74 | System Limitation
ISS-2015 | CTRL-1043 | Missing Review Evidence | Delayed Approval Workflow identified during recurring control monitoring activities. | High | Open | Skyler Williams | Operations | 2025-12-06 | 2026-01-05 | 185 | Human Error
ISS-2016 | CTRL-1024 | Manual Process Dependency | Manual Process Dependency identified during recurring control monitoring activities. | High | Open | Casey Lewis | Risk Management | 2026-04-02 | 2026-07-01 | 68 | Human Error
ISS-2017 | CTRL-1018 | Control Owner Attestation Missing | Missing Review Evidence identified during recurring control monitoring activities. | High | Past Due | Kendall Garcia | Finance | 2025-10-16 | 2025-11-30 | 236 | Resource Constraint
ISS-2018 | CTRL-1001 | Access Review Not Completed | Access Review Not Completed identified during recurring control monitoring activities. | High | Remediated | Logan Jackson | Technology | 2026-04-22 | 2026-08-20 | 108 | Policy Misalignment
ISS-2019 | CTRL-1047 | Data Validation Exception | Recovery Procedure Gap identified during recurring control monitoring activities. | Medium | In Progress | Drew Smith | Finance | 2026-04-29 | 2026-06-13 | 41 | Resource Constraint
ISS-2020 | CTRL-1008 | Manual Process Dependency | Manual Process Dependency identified during recurring control monitoring activities. | Low | Open | Riley Clark | Risk Management | 2026-02-19 | 2026-05-20 | 110 | Data Quality Issue
ISS-2021 | CTRL-1049 | Incomplete Control Documentation | Late Remediation Action identified during recurring control monitoring activities. | Medium | Remediated | Taylor Jackson | Operations | 2025-12-10 | 2026-01-24 | 75 | Process Gap
ISS-2022 | CTRL-1030 | Unresolved System Exception | Incomplete Control Documentation identified during recurring control monitoring activities. | Medium | Open | Emerson Jackson | Enterprise Resilience | 2026-03-26 | 2026-07-24 | 75 | Data Quality Issue
ISS-2023 | CTRL-1033 | Manual Process Dependency | Unresolved System Exception identified during recurring control monitoring activities. | Critical | Open | Cameron Johnson | Finance | 2026-03-27 | 2026-06-25 | 74 | System Limitation
ISS-2024 | CTRL-1027 | Delayed Approval Workflow | Late Remediation Action identified during recurring control monitoring activities. | Medium | Closed | Quinn Harris | Finance | 2025-10-17 | 2025-12-16 | 73 | Policy Misalignment
ISS-2025 | CTRL-1008 | Control Owner Attestation Missing | Delayed Approval Workflow identified during recurring control monitoring activities. | Critical | Open | Rowan Martin | Enterprise Resilience | 2026-03-01 | 2026-05-30 | 100 | Data Quality Issue
ISS-2026 | CTRL-1004 | Control Owner Attestation Missing | Delayed Approval Workflow identified during recurring control monitoring activities. | Medium | Past Due | Drew Lewis | Operations | 2026-04-05 | 2026-08-03 | 65 | Resource Constraint
ISS-2027 | CTRL-1010 | Incomplete Control Documentation | Data Validation Exception identified during recurring control monitoring activities. | Low | Open | Skyler Williams | Treasury | 2026-02-28 | 2026-04-29 | 101 | Resource Constraint
ISS-2028 | CTRL-1027 | Delayed Approval Workflow | Missing Review Evidence identified during recurring control monitoring activities. | High | Closed | Dylan Taylor | Compliance | 2025-12-23 | 2026-04-22 | 37 | Human Error
ISS-2029 | CTRL-1014 | Manual Process Dependency | Access Review Not Completed identified during recurring control monitoring activities. | Medium | Open | Drew Wilson | Operations | 2025-12-05 | 2026-02-03 | 186 | Policy Misalignment
ISS-2030 | CTRL-1031 | Control Owner Attestation Missing | Incomplete Control Documentation identified during recurring control monitoring activities. | Critical | In Progress | Harper Jackson | Operations | 2026-02-14 | 2026-06-14 | 115 | Human Error
ISS-2031 | CTRL-1040 | Unresolved System Exception | Data Validation Exception identified during recurring control monitoring activities. | High | Closed | Cameron Martinez | Technology | 2026-03-30 | 2026-05-29 | 68 | Resource Constraint
ISS-2032 | CTRL-1036 | Access Review Not Completed | Recovery Procedure Gap identified during recurring control monitoring activities. | High | Open | Logan White | Enterprise Resilience | 2026-05-04 | 2026-06-03 | 36 | Process Gap
ISS-2033 | CTRL-1022 | Manual Process Dependency | Recovery Procedure Gap identified during recurring control monitoring activities. | Medium | Closed | Harper Anderson | Finance | 2026-04-01 | 2026-07-30 | 27 | Policy Misalignment
ISS-2034 | CTRL-1035 | Unresolved System Exception | Manual Process Dependency identified during recurring control monitoring activities. | Medium | Remediated | Morgan Moore | Treasury | 2026-02-04 | 2026-03-06 | 90 | System Limitation
ISS-2035 | CTRL-1029 | Delayed Approval Workflow | Manual Process Dependency identified during recurring control monitoring activities. | High | Remediated | Jamie Harris | Technology | 2026-01-06 | 2026-05-06 | 48 | Process Gap
ISS-2036 | CTRL-1024 | Delayed Approval Workflow | Control Owner Attestation Missing identified during recurring control monitoring activities. | High | Open | Riley Wilson | Technology | 2025-09-04 | 2026-01-02 | 278 | System Limitation
ISS-2037 | CTRL-1022 | Delayed Approval Workflow | Control Owner Attestation Missing identified during recurring control monitoring activities. | Critical | Closed | Harper Martin | Risk Management | 2026-02-06 | 2026-05-07 | 77 | Policy Misalignment
ISS-2038 | CTRL-1045 | Unresolved System Exception | Incomplete Control Documentation identified during recurring control monitoring activities. | Critical | Remediated | Taylor Johnson | Technology | 2025-12-08 | 2026-01-22 | 54 | Policy Misalignment
ISS-2039 | CTRL-1049 | Recovery Procedure Gap | Missing Review Evidence identified during recurring control monitoring activities. | Critical | In Progress | Jordan Garcia | Finance | 2025-11-18 | 2026-01-17 | 203 | Policy Misalignment
ISS-2040 | CTRL-1017 | Manual Process Dependency | Control Owner Attestation Missing identified during recurring control monitoring activities. | Low | Open | Taylor Martinez | Treasury | 2025-11-19 | 2026-03-19 | 202 | Data Quality Issue
ISS-2041 | CTRL-1026 | Unresolved System Exception | Incomplete Control Documentation identified during recurring control monitoring activities. | High | Past Due | Alex Williams | Technology | 2025-10-15 | 2026-01-13 | 237 | Human Error
ISS-2042 | CTRL-1006 | Late Remediation Action | Access Review Not Completed identified during recurring control monitoring activities. | Critical | Past Due | Parker Smith | Finance | 2025-12-04 | 2026-01-18 | 187 | Resource Constraint
ISS-2043 | CTRL-1002 | Manual Process Dependency | Recovery Procedure Gap identified during recurring control monitoring activities. | Medium | In Progress | Harper Anderson | Finance | 2025-09-05 | 2025-11-04 | 277 | Resource Constraint
ISS-2044 | CTRL-1032 | Data Validation Exception | Missing Review Evidence identified during recurring control monitoring activities. | Low | Open | Avery Williams | Risk Management | 2025-09-01 | 2025-11-30 | 281 | System Limitation
ISS-2045 | CTRL-1017 | Incomplete Control Documentation | Delayed Approval Workflow identified during recurring control monitoring activities. | Critical | Open | Jamie Garcia | Operations | 2026-03-08 | 2026-06-06 | 93 | Data Quality Issue
ISS-2046 | CTRL-1012 | Access Review Not Completed | Manual Process Dependency identified during recurring control monitoring activities. | High | In Progress | Taylor Williams | Treasury | 2025-09-28 | 2026-01-26 | 254 | Data Quality Issue
ISS-2047 | CTRL-1046 | Recovery Procedure Gap | Access Review Not Completed identified during recurring control monitoring activities. | High | In Progress | Taylor Robinson | Treasury | 2026-02-17 | 2026-04-18 | 112 | Human Error
ISS-2048 | CTRL-1038 | Data Validation Exception | Incomplete Control Documentation identified during recurring control monitoring activities. | Low | Past Due | Logan Lewis | Enterprise Resilience | 2025-10-11 | 2026-01-09 | 241 | Resource Constraint
ISS-2049 | CTRL-1009 | Access Review Not Completed | Data Validation Exception identified during recurring control monitoring activities. | High | Remediated | Emerson Williams | Operations | 2026-05-03 | 2026-06-02 | 119 | Resource Constraint
ISS-2050 | CTRL-1050 | Unresolved System Exception | Missing Review Evidence identified during recurring control monitoring activities. | Critical | Open | Parker Lewis | Enterprise Resilience | 2025-10-10 | 2026-01-08 | 242 | Resource Constraint
ISS-2051 | CTRL-1011 | Control Owner Attestation Missing | Recovery Procedure Gap identified during recurring control monitoring activities. | Medium | Open | Drew Davis | Treasury | 2025-11-24 | 2026-03-24 | 197 | Human Error
ISS-2052 | CTRL-1034 | Missing Review Evidence | Delayed Approval Workflow identified during recurring control monitoring activities. | High | Past Due | Avery Williams | Compliance | 2025-10-29 | 2026-02-26 | 223 | Human Error
ISS-2053 | CTRL-1032 | Manual Process Dependency | Missing Review Evidence identified during recurring control monitoring activities. | Medium | Past Due | Taylor Harris | Risk Management | 2025-12-15 | 2026-01-29 | 176 | Resource Constraint
ISS-2054 | CTRL-1018 | Recovery Procedure Gap | Access Review Not Completed identified during recurring control monitoring activities. | Medium | Open | Casey Thomas | Risk Management | 2025-09-19 | 2026-01-17 | 263 | Resource Constraint
ISS-2055 | CTRL-1035 | Unresolved System Exception | Recovery Procedure Gap identified during recurring control monitoring activities. | Medium | Open | Kendall Miller | Risk Management | 2025-11-09 | 2026-02-07 | 212 | Data Quality Issue
ISS-2056 | CTRL-1007 | Recovery Procedure Gap | Data Validation Exception identified during recurring control monitoring activities. | Low | Remediated | Drew Robinson | Treasury | 2026-01-07 | 2026-04-07 | 76 | Resource Constraint
ISS-2057 | CTRL-1006 | Manual Process Dependency | Data Validation Exception identified during recurring control monitoring activities. | Low | Open | Kendall Brown | Enterprise Resilience | 2026-01-20 | 2026-03-21 | 140 | Data Quality Issue
ISS-2058 | CTRL-1021 | Delayed Approval Workflow | Delayed Approval Workflow identified during recurring control monitoring activities. | Medium | Open | Taylor Moore | Enterprise Resilience | 2025-11-06 | 2026-03-06 | 215 | Process Gap
ISS-2059 | CTRL-1025 | Recovery Procedure Gap | Late Remediation Action identified during recurring control monitoring activities. | High | Remediated | Riley Brown | Enterprise Resilience | 2025-11-25 | 2026-02-23 | 17 | Resource Constraint
ISS-2060 | CTRL-1030 | Unresolved System Exception | Recovery Procedure Gap identified during recurring control monitoring activities. | Critical | Open | Rowan Johnson | Technology | 2025-11-01 | 2025-12-31 | 220 | System Limitation
ISS-2061 | CTRL-1026 | Delayed Approval Workflow | Unresolved System Exception identified during recurring control monitoring activities. | High | Remediated | Quinn Williams | Technology | 2025-10-20 | 2026-01-18 | 113 | Process Gap
ISS-2062 | CTRL-1011 | Unresolved System Exception | Delayed Approval Workflow identified during recurring control monitoring activities. | High | Open | Riley Clark | Treasury | 2025-10-09 | 2025-11-08 | 243 | System Limitation
ISS-2063 | CTRL-1008 | Missing Review Evidence | Access Review Not Completed identified during recurring control monitoring activities. | Low | Past Due | Emerson Martin | Risk Management | 2026-01-11 | 2026-04-11 | 149 | Resource Constraint
ISS-2064 | CTRL-1029 | Delayed Approval Workflow | Late Remediation Action identified during recurring control monitoring activities. | Medium | Open | Logan Moore | Finance | 2025-11-09 | 2026-01-08 | 212 | Process Gap
ISS-2065 | CTRL-1045 | Late Remediation Action | Late Remediation Action identified during recurring control monitoring activities. | Medium | Open | Parker Harris | Technology | 2026-03-29 | 2026-05-13 | 72 | Process Gap
ISS-2066 | CTRL-1007 | Delayed Approval Workflow | Recovery Procedure Gap identified during recurring control monitoring activities. | High | Past Due | Jordan Davis | Treasury | 2025-10-25 | 2025-12-09 | 227 | Data Quality Issue
ISS-2067 | CTRL-1044 | Unresolved System Exception | Recovery Procedure Gap identified during recurring control monitoring activities. | Low | Past Due | Taylor Clark | Operations | 2026-04-23 | 2026-05-23 | 47 | Human Error
ISS-2068 | CTRL-1009 | Unresolved System Exception | Manual Process Dependency identified during recurring control monitoring activities. | High | Open | Dylan Smith | Technology | 2026-03-25 | 2026-05-09 | 76 | Human Error
ISS-2069 | CTRL-1018 | Incomplete Control Documentation | Recovery Procedure Gap identified during recurring control monitoring activities. | High | Open | Logan Taylor | Finance | 2025-11-17 | 2026-02-15 | 204 | System Limitation
ISS-2070 | CTRL-1033 | Late Remediation Action | Late Remediation Action identified during recurring control monitoring activities. | Low | Past Due | Rowan Clark | Risk Management | 2026-01-04 | 2026-05-04 | 156 | Process Gap
ISS-2071 | CTRL-1035 | Manual Process Dependency | Data Validation Exception identified during recurring control monitoring activities. | Medium | In Progress | Parker Johnson | Technology | 2025-10-10 | 2026-02-07 | 242 | Data Quality Issue
ISS-2072 | CTRL-1047 | Incomplete Control Documentation | Late Remediation Action identified during recurring control monitoring activities. | Medium | Remediated | Taylor Robinson | Risk Management | 2026-04-14 | 2026-06-13 | 29 | Resource Constraint
ISS-2073 | CTRL-1023 | Access Review Not Completed | Delayed Approval Workflow identified during recurring control monitoring activities. | Low | In Progress | Cameron Davis | Compliance | 2026-01-08 | 2026-02-22 | 152 | Resource Constraint
ISS-2074 | CTRL-1029 | Late Remediation Action | Missing Review Evidence identified during recurring control monitoring activities. | Critical | Remediated | Emerson Smith | Compliance | 2025-11-22 | 2026-03-22 | 72 | Policy Misalignment
ISS-2075 | CTRL-1038 | Recovery Procedure Gap | Delayed Approval Workflow identified during recurring control monitoring activities. | High | Open | Kendall Smith | Enterprise Resilience | 2026-01-20 | 2026-03-06 | 140 | System Limitation
ISS-2076 | CTRL-1037 | Incomplete Control Documentation | Incomplete Control Documentation identified during recurring control monitoring activities. | Critical | Open | Parker Johnson | Operations | 2025-11-30 | 2026-02-28 | 191 | Resource Constraint
ISS-2077 | CTRL-1044 | Unresolved System Exception | Access Review Not Completed identified during recurring control monitoring activities. | Critical | Past Due | Jamie Clark | Treasury | 2025-10-06 | 2025-12-05 | 246 | Process Gap
ISS-2078 | CTRL-1004 | Data Validation Exception | Control Owner Attestation Missing identified during recurring control monitoring activities. | Critical | In Progress | Taylor Robinson | Compliance | 2026-04-29 | 2026-06-28 | 41 | Policy Misalignment
ISS-2079 | CTRL-1036 | Data Validation Exception | Access Review Not Completed identified during recurring control monitoring activities. | High | Open | Jamie Davis | Finance | 2026-01-22 | 2026-03-08 | 138 | Process Gap
ISS-2080 | CTRL-1038 | Incomplete Control Documentation | Access Review Not Completed identified during recurring control monitoring activities. | High | Open | Parker Brown | Compliance | 2025-09-09 | 2025-10-24 | 273 | Human Error
ISS-2081 | CTRL-1035 | Incomplete Control Documentation | Manual Process Dependency identified during recurring control monitoring activities. | Critical | Closed | Jordan Jackson | Technology | 2025-12-11 | 2026-03-11 | 40 | Policy Misalignment
ISS-2082 | CTRL-1047 | Delayed Approval Workflow | Recovery Procedure Gap identified during recurring control monitoring activities. | High | In Progress | Riley Smith | Compliance | 2026-02-05 | 2026-04-06 | 124 | Human Error
ISS-2083 | CTRL-1017 | Missing Review Evidence | Manual Process Dependency identified during recurring control monitoring activities. | Critical | Closed | Avery Garcia | Compliance | 2025-12-16 | 2026-02-14 | 62 | Human Error
ISS-2084 | CTRL-1021 | Unresolved System Exception | Recovery Procedure Gap identified during recurring control monitoring activities. | Low | Open | Emerson Garcia | Risk Management | 2025-11-29 | 2026-02-27 | 192 | Data Quality Issue
ISS-2085 | CTRL-1046 | Delayed Approval Workflow | Missing Review Evidence identified during recurring control monitoring activities. | Medium | Remediated | Parker Garcia | Treasury | 2025-12-15 | 2026-03-15 | 46 | Process Gap
ISS-2086 | CTRL-1001 | Access Review Not Completed | Missing Review Evidence identified during recurring control monitoring activities. | High | Closed | Avery Robinson | Operations | 2025-09-04 | 2025-10-04 | 79 | Policy Misalignment
ISS-2087 | CTRL-1045 | Recovery Procedure Gap | Manual Process Dependency identified during recurring control monitoring activities. | Medium | Closed | Taylor Moore | Compliance | 2026-01-30 | 2026-03-16 | 100 | System Limitation
ISS-2088 | CTRL-1029 | Control Owner Attestation Missing | Delayed Approval Workflow identified during recurring control monitoring activities. | Medium | Closed | Cameron Wilson | Technology | 2025-12-12 | 2026-01-26 | 117 | Process Gap
ISS-2089 | CTRL-1004 | Data Validation Exception | Unresolved System Exception identified during recurring control monitoring activities. | Low | Open | Harper Robinson | Finance | 2026-02-23 | 2026-04-09 | 106 | Resource Constraint
ISS-2090 | CTRL-1018 | Data Validation Exception | Manual Process Dependency identified during recurring control monitoring activities. | Low | Open | Reese Williams | Compliance | 2025-11-16 | 2025-12-16 | 205 | Policy Misalignment
ISS-2091 | CTRL-1015 | Recovery Procedure Gap | Missing Review Evidence identified during recurring control monitoring activities. | Low | Open | Quinn White | Treasury | 2025-10-30 | 2026-02-27 | 222 | Data Quality Issue
ISS-2092 | CTRL-1008 | Recovery Procedure Gap | Manual Process Dependency identified during recurring control monitoring activities. | Low | Past Due | Reese Lewis | Treasury | 2026-01-06 | 2026-03-07 | 154 | Resource Constraint
ISS-2093 | CTRL-1026 | Unresolved System Exception | Access Review Not Completed identified during recurring control monitoring activities. | Critical | Open | Morgan Thomas | Risk Management | 2025-10-27 | 2025-12-26 | 225 | Data Quality Issue
ISS-2094 | CTRL-1032 | Missing Review Evidence | Missing Review Evidence identified during recurring control monitoring activities. | Medium | Past Due | Quinn Anderson | Compliance | 2026-01-31 | 2026-04-01 | 129 | Human Error
ISS-2095 | CTRL-1022 | Missing Review Evidence | Access Review Not Completed identified during recurring control monitoring activities. | Low | Remediated | Casey Jackson | Compliance | 2026-04-16 | 2026-07-15 | 106 | Resource Constraint
ISS-2096 | CTRL-1034 | Delayed Approval Workflow | Data Validation Exception identified during recurring control monitoring activities. | High | Open | Emerson Brown | Risk Management | 2025-09-14 | 2025-10-29 | 268 | Data Quality Issue
ISS-2097 | CTRL-1017 | Recovery Procedure Gap | Delayed Approval Workflow identified during recurring control monitoring activities. | High | Open | Parker Brown | Treasury | 2026-04-26 | 2026-06-10 | 44 | System Limitation
ISS-2098 | CTRL-1001 | Recovery Procedure Gap | Delayed Approval Workflow identified during recurring control monitoring activities. | Low | Remediated | Taylor Smith | Enterprise Resilience | 2026-01-15 | 2026-03-01 | 104 | Human Error
ISS-2099 | CTRL-1031 | Recovery Procedure Gap | Access Review Not Completed identified during recurring control monitoring activities. | Critical | Past Due | Avery Williams | Risk Management | 2026-01-20 | 2026-05-20 | 140 | Process Gap
ISS-2100 | CTRL-1047 | Missing Review Evidence | Recovery Procedure Gap identified during recurring control monitoring activities. | Critical | Open | Parker Garcia | Compliance | 2026-04-19 | 2026-06-03 | 51 | Policy Misalignment